Rebecca E. Skinner
Project Leader, Manylabs / SFAQ

info@sanfranciscoaq.org  
   						November 24, 2025

DRAFT
Final Report 2025: Air Quality Network for San Francisco’s Eastern Neighborhoods

Table of Contents

Air Quality Network for San Francisco Eastern Neighborhoods

List of Figures and Photographs

Map of San Francisco

Map of the Eastern Neighborhoods

Planning Department Air Pollution Exposure Zone Map

Map of Monitoring Sites- Entire City

Map of Monitoring Sites- Eastern Neighborhoods

Photos of the Equipment – Sensit SPOD

Photos of the Equipment – Purple Air

Goettingen Street Portola
Hudson Street 
Newcomb Street
Paul and Bayshore 
Boedekker Park, 196 Eddy Street

175 Golden Gate Avenue

Geneva and Mission 
Cargo Way

1. Brief Summary

2. Problem Definition 
2.1 The Problem of Ambient VOCs

3. The Development of San Francisco in Context of Land Use and Aerosols

4. Project Description
4.1 Technical Approach
4.2 Sensor Instrumentation Plan

4.3 Initial Co-location
4.4 Data plan QA-QC

5. Implementation, and Issues therein

6. Report on the Data

6.1 Report on the Data - Summary

Brief Comparative Analysis (Two Pages) a Sensit Connect chart, saved as screenshot PNG;

6.2 Exposition regarding Different Locations

1. 48th Ave at Kirkham

2. Crane Street- Paul at Bayshore

3. 1700 Block, Newcomb Street at Phelps
4. The Portola: Goettingen Street at Wayland

5. Hudson at Mendell Street

6. Mobile day deployments: Boedekker Park and 175 Golden Gate Avenue

7. BVHP mobile day deployments: 1550 Evans at Newhall

8. BVHP mobile day deployments at 3rd and Cargo Way

9. Geneva and Mission

6.3 Summary Statistics and Time Series Averages

6.4 Diurnal Trends

6.5 Correlation: TVOC Levels with Temperature, RH, mBar Pressure and Wind Speed

7. Conclusion and Policy Suggestions

7.1 Significance of the Findings

7.2 The Way Forward: Monitoring Suggestions

7.3 Policy Suggestions

8. References 
9. Appendices:

9.1 Diurnal Trends

9.2 Data for Correlation Study

9.3 Governmental Air Quality Guidelines for VOCs

9.4 List of California TACs.
9.5 SF City Maps

10. Acknowledgements

1. Brief Summary

   San Francisco-based open science non-profit Manylabs/ San Francisco AQ’s Air Quality Network for San Francisco’s Eastern Neighborhoods, submitted to the California Air Resources Board, is a Supplemental Environmental Project. The project staff installs, maintains, and displays information online for air quality monitoring instrumentation to detect particulate matter 2.5 (PM 2.5) and Volatile Organic Compounds. PM 2.5 contributes to pulmonary and cardiovascular illnesses, and VOCs such as benzene, formaldehyde, and carbon tetrachloride inflict various health effects such as headaches, coughing and irregular heartbeat, and pose an incremental cancer risk. 

   This project builds upon the work of an earlier SEP grant, which deployed monitors in the Eastern Neighborhoods, encompassing Bayview-Hunters Point, the Excelsior, Bernal Heights, Visitacion Valley, Portola, Balboa Park, the Dogpatch, and the Tenderloin and Chinatown.

Technical Approach

Our original focus on PM 2.5 monitoring was revised in light of new developments between the original approval and the time that the project was funded. AB617 legislation, assertively implemented, has provided funding and support to PM 2.5 monitoring funding for numerous California environmental justice communities, and required that they implement PM 2.5 monitoring, pandemics notwithstanding. 

   The progress made by community-based organizations such as Greenaction, the Marie Harrison Bayview Air Monitoring Project, and All Things Bayview has alleviated the need for hyperlocal PM 2.5 monitoring in the Eastern Neighborhoods. The project has two Purple Air II monitors remaining and are working with CBOs to deploy them in the Bayview. 

    Alterations to the original plans, confirmed in discussions with the Air Resources Board, allowed increased focus on VOCs, the carcinogenic properties of which are confirmed in the Federal NESHAPs and state's Toxic Air Contaminants inventory. Vinyl Chloride and H2s are measured in CARB lists, and H2S is measured at certain BAAQMD Federal Reference Method centers (Richmond, Point Richmond, and Rodeo).  However, the photo-ionization detectors required for VOC detection remain expensive, and such instrumentation has not typically been used in community air monitoring projects.

Method of Inquiry
   We obtained five Sensit brand SPOD non-regulatory instruments. These units have a photo ionization detector (PID) for VOC level determination, a GPS, and a small weather unit attached to assess Temperature, RH, wind speed, bearing, and geographic location. These were deployed and gathered data for more than a year, in the Portola, central Bayview Hunters Point, and southern Bayview near San Bruno Avenue. One unit in the Outer Sunset neighborhood served as a control, and another was used for temporary deployments in various locations in the Tenderloin and the Outer Mission. Sensit Connect software manages data logging, and we are using Excel, CSV files, and Google Sheets for data analysis and graphing. We displayed this data on the sanfranciscoaq.org website and presented it at community meetings. 

Preliminary Findings
   We have found a secular trend of consistently high background TVOC levels in the central and southern BVHP in areas adjacent to high VMT and industrial infrastructure, and at sidewalk streetside locations in the Tenderloin and the Outer Mission. We have also found higher diurnal discrepancies (over the course of a day) in the former areas. None of these levels reached OSHA’s 8-hour proscribed levels, but many levels were not far short of it.

Background Aerosol Pollutant Levels

The most persistently high TVOC levels among the longer deployments were on a short street a tenth of a mile from Paul Avenue, the old Bayshore Boulevard, and Highway 101. Source attribution is a fairly straightforward conclusion, given the proximity to a busy street linking San Bruno Avenue with Southern Bayview, and two major north-south vehicle routes. For the first several months of our study, there was also diesel exhaust blast when the industrial data center nearby shuts on and off during shift changed. 

   The next highest levels were in central Bayview, 1/10ths of a mile from the Water Treatment Plant currently under reconstruction. For the purpose of this report, we define the Bayview Opera House as the center point in Bayview Hunter's Point. Persistently high TVOC levels in central Bayview suggest high background levels throughout the neighborhood. The unit near the Water Treatment Plant is in the middle of a tree-filled backyard behind a two-story building on a deep lot, and thus relatively protected from street traffic.

Another morning sidewalk deployment at Cargo Way and Third Street, on June 21, 2024, was sufficiently noxious that the participants had to stop the test, dismantle the equipment, and leave the area within an hour, even as the TVOC levels continued to increase. Granted, this location is not a residential street. However, it is on a major arterial route with bus and light rail traffic into and from the Bayview, especially during commute hours. In addition, it is .9 miles north of central Bayview.

Sidewalk Pollutant versus Backyard Deployments
   Notwithstanding these higher background levels in light industrial and transit corridor areas, there are relatively lower levels of pollutants in backyards with significant vegetation. This is true in a unit on a residential street six-tenths of a mile from the Cargo Way site. However, the 1550 Evans Street sidewalk deployment, further from the heavy industrial sites at Cargo Way, Amador Street, and Pier 80, had little street vehicular traffic and did not evidence high TVOCs. 

   The most minimal TVOC levels were found in the six-month backyard deployment on Goettingen Street near Wayland Street. This hosting site, which ran from June, 2023 through January, 2024, showed such consistently low readings that the unit was removed. 

   Another site with consistently and unexpectedly moderate TVOC levels was Boedekker Park, at Eddy and Jones Street, where daytime community monitoring was carried out in March, June, and September 2024. The designated spot for monitoring in the Park was roughly seventy feet from the sidewalk. However, subsequent testing on the sidewalk a few hundred feet away at 175 Golden Gate at Eddy yielded far higher pollutant levels. This was tested both in the morning and the afternoon. Another site at the intersection of Geneva and Mission, a busy Outer Mission intersection for buses, cars, trucks, and pedestrians, had high TVOC levels. 

Construction, Street Traffic, and Barbeques
  The control unit was located about ten feet above the sidewalk on a fenced second-floor patio facing the street at 48th Avenue and Kirkham in the Sunset. This unit had well-known point sources, in the form of a neighbor’s sidewalk barbeque and campfire location across the street to the east. These inflict weekly TVOC spikes on the immediate area. (SFPD will not ticket a cooking fire contained with any sort of built structure, even a home-made sidewalk fire pit). Starting in December of 2024, ongoing construction of ADU units in a multifamily apartment building to the northeast also was accompanied by increased TVOC ppb readings. 

2. Problem Definition

This project is an open-ended exploration of the TVOC levels in the Eastern Neighborhoods..

If open-ended, our aims were not aimless. There is much extant data regarding AQ in the Eastern Neighborhoods and especially in the Bayview. Thus our locations of interest were well-defined early on by community ground-truth. The excessive burden of NAAQS pollutants is a matter of public record according to both agencies and the community. We also wished to discern any TVOC levels proximate to sensitive receptors, locations of high VMT, and permitted stationary sources.

2.1 The Problem of Ambient VOCs

The problem is not only finding out levels of TVOC at the given locations, but also of putting this information in context of epidemiological knowledge regarding the danger of such aerosols.

Volatile Organic Compounds are easily volatilized non-methane hydrocarbons (NMHC). Methane (CH4) is indeed a volatile hydrocarbon, but VOCs are usually heavier molecules.

More precisely, they are organic carbon chain or ring-based compounds which readily evaporate at room temperature, with a vapor pressure over 2mm mercury HG, (0.27kPa) at 25 degrees Celsius. Volatile organic compounds (VOCs) are also defined as those which have a Reid vapor pressure above 10.3 Pa at ambient temperature (293.15 K) and pressure (101.325 kPa) . The US EPA’s definition narrows the scope slightly:

“Volatile organic compounds (VOCs) are defined as any compound of carbon, excluding carbon monoxide, carbon dioxide, carbonic acid, metallic carbides or carbonates, and ammonium carbonate, which participates in atmospheric photochemical reactions”,.

Zhang et al.’s 2017 survey article indicates that the definition of VOC varies across nations and agencies, “but all have the general characteristics of low boiling point, high vapor pressure, and strong reactivity, especially with respect to photochemical reactions.”  These features describe a long list; Zhang indicates that there are more than 300 species of VOCs.

The dangers of volatile organic compounds are not unknown. Toxic Air Contaminants, or TACs, are a subset of VOCs specifically indicated as those harmful to human health (See Appendix 9.4 List of California TACs). Dozens of VOCs are designated Hazardous Air Pollutants, or HAPs (or toxic air pollutants), for which the EPA has set no safe threshold level of exposure. To make matters more complex, California’s Air Resources Board refers to the 189 federal HAPs (and a few others) as Toxic Air Contaminants (TACs). TACs and HAPs are thus a subset of VOCs, and all TACs/ HAPs are VOCs, but not all VOCs are TACs. 

   VOCs are a far wider inventory, including biological species as mentioned. Recently, they have been attracting more study in the published scientific literature. VOCs are lipo-philicitous, readily dissolving in fat, oil, or non-polar solvents, and are thus readily absorbed by lungs, skin, and gastrointestinal tract. These are not innocuous bad odors, but serious carcinogens for which no minimum level has been determined to be safe,,. VOCs cause any number of severe health problems, , as well as sub-clinical conditions, which commonly result in interruptions to work, sleep, or leisure rather than a visit to the physician. These include neurological effects (toluene, in nail products); irregular heartbeat and myeloid leukemia (benzene); CNS disorders (styrene), irritation of respiratory tract and eyes (ketones, alcohols, formaldehyde, undecane and nonane), and peripheral neuropathy (hexane). TVOCs, such as the cocktail of contaminants in ‘sick buildings’, contribute to sensory irritation, headache and fatigue. The U.S. National Air Toxics Assessment recognizes formaldehyde, 1,3- butadiene, and benzene as national cancer risk drivers and contributors.  In addition to household products such as HCOH in cleaning supplies and IAQ, most people encounter VOCs through proximity to ICE engine vehicles.

The Agency for Toxic Substances and Disease Registry at the Centers for Disease Control maintains exhaustive online epidemiological data for each TAC. TACs are tracked by the California EPA's Office of Environmental Health Hazards Assessment (OEHHA), as well as by the EU and the WHO.  They are well-understood in environmental health, and increasingly studied, . Yet much of their regulation is overseen and enforced, in a mottled and uneven manner, at the state and local level.

For the purposes of enforcement- rather than public health study- VOCs are not accorded the gravity they merit.  Yet VOCs are an increasing threat in a world with secular trend of higher temperatures. Moreover, as Ozone precursors they contribute to O3 production as a secondary aerosol in the presence of NO and sunlight .

That VOCs are harmful to human health is beyond any doubt. Their relative danger upon exposure is a matter of controversy. Governmental regulatory standards for TVOCs are usually for closed workplaces, rather than general ambient aerosol standards, because of aerosol dispersal with mass transport. The United States response has been uneven in the formation of rules, and weaker in their implementation. However, Volatile organic compounds are taken seriously in Europe in both regulations and enforcement:

“The World Health Organization (WHO) Air Quality Guideline for Europe [in 2000] establishes guideline values for toluene, 260 ug/m3 over 1 week, for formaldehyde, 100ug/m3 over 30 min and for tetrachloroethylene, 250 ug/m3 over 1 year. Additionally, it sets the guideline values for benzene corresponding to the concentration levels associated with an excess lifetime risk of 1/10,000, 1/100,000 and 1/1,000,000 equal to 17, 1.7, and 0.17 ug/m3, respectively. In 2010, the WHO Guidelines for Air Quality in Indoor Air confirmed the guideline values given in 2000 for benzene… the European Air Quality Directive AQD defines as mandatory the monitoring of benzene in ambient air. The AQD states that the reference method for the measurement of BTEX consists of active or online sampling followed by desorption and gas chromatography.”

However, there are as mentioned inordinate health effects on environmental justice neighborhoods.  There are also and innumerable environments outside California- both in the USA and beyond- in which criteria pollutants are ignored, and the idea of regulating TAC emissions sounds like an idealistic fantasy.  As the human cost is increasingly taken seriously, we anticipate that the cost of VOC emissions mitigation will increasingly seem less and less expensive.  Notwithstanding this prognostication, it has not happened yet, and we recognize that EJ communities are on their own.

However, increased implementation of ambient standards is salient, both in international standards for ambient and IAQ VOCs, and in US architectural and construction codes.

WHO Air Quality Guideline:

>0.10 ppm to 0.20 harmless;
>0.20 ppm to 0.61 temporary exposure only;

.20 ppm is 200 ppb; 61 ppm is 610 ppb;

Well Building Standard TVOC  <500 ug/m3, , < 0.25 ppm

Atmotube: “Translation from mass concentration ug/m3 to particle concentration ppb is based on an average molar mass of TVOC molecules, according the TVOC mix proposed by Molhave 1997. Thereby 4.9 ug/m3 corresponds to 1 ppb TVOC concentration.”

Common TACs that we would be concerned with are related to the running, maintenance, and repair of internal combustion engines, and combustion in industrial processes in permitted facilities in the EN. These can be found in the EPA’s TO-14 and TO-15 analytical lab tests, for most common ambient VOCs found inside and outside buildings, respectively. Unlike NAAQS pollutants, TACs do not have attached specific prohibited levels at relatively low ambient concentrations. This does not mean that cumulative effects do not exist for ongoing low-levels of exposure.

3. The Development of San Francisco in Context of Land Use and Aerosols

Air quality in the Eastern Neighborhoods have been an ongoing topic of interest. No surprise here: paradoxically, both the greater part of the functionality of the City, as well as the majority of its pollution burden, is concentrated in the Eastern Neighborhoods. These are difficult to extricate, since industry and construction involve the combustion of carbon and the manipulation of physical material in a way that carbon is emitted.

The history of the Eastern Neighborhoods, which we will briefly consider, helps to explain the areas’ chronic Air Quality issues. Intense, sudden economic activity transformed the original port and tiny village of Yerba Buena Cove into the city of San Francisco. The essential catalytic event was the discovery of gold at Sutter’s Mill in 1848, the same year that California was ceded to the United States. The frenzy of Gold Rush ship arrivals within the next two years did not last, especially after the Transcontinental Railway made the journey from the East Coast much faster and less hazardous in 1871. Between forty and seventy abandoned ships from the Gold Rush are buried throughout the Financial District as far west as the site of the Transamerica Pyramid, Soma, Folsom and Main Streets, west to Battery and Filbert Streets in North Beach. The Port of San Francisco remains https://www.nps.gov/safr/learn/historyculture/buried-ships-of-san-francisco.html.

The city grew in three dimensions, as solid ground emerged from wetlands and open water. Much of the Financial District, the Marina, the area of the Bayview near Islais Creek and Yosemite Slough, and Mission Bay as far inland as 16th and 7th Streets, were originally underwater (see SF Water Power Sewer 100-Year Storm Flood Risk Map). Landfill filled in much of the Eastern bay, as far south as the Brisbane Baylands. Garbage was dumped directly into the Bay as late as the 1960s. The railway lines which California depended on until trucks and cars triumphed in the 20th Century, were built in vast acreage, again on the eastern side. Rail yards covered the current site of the Caltrain terminus and the Mission Bay UCSF campus and adjacent brand-new neighborhood. With a far smaller footprint, Caltrain remains, with the 4th and Townsend terminal Station, the 22nd Street station, and the forlorn Bayshore station near Geneva and Tunnel Avenues. The Southern Pacific rail yards, adjacent to Geneva and Bayshore Avenues, were left to go to seed as fenced-off open space. 

   By the third decade of the 20th century, cars and trucks won the contest over major transportation method, and rail was relegated to a very much second-place. Highway transit lines were expanded in mid-century. Highway 101, built in 1954, parallels the city’s original Bayshore Route, as does Caltrain. The mid-60s saw the construction of the I-280 freeway, which cuts from the Caltrain terminus, parallels the route of Mission Street to Daly City, and continues as Junipero Serra Boulevard to points south on the Peninsula. While mostly forgotten, the Embarcadero Freeway (Interstate 480), ran north as far as Broadway, cutting off light and impeding access to the Embarcadero and Broadway. Universally derided, the elevated multi-level freeway was torn down after it was damaged during the 1989 Loma Prieta Earthquake. 

    Land use under California’s ownership by Mexico had been land-grant ranchos, covering almost the entirety of the City, along with the largely abandoned Presidio and Mission Dolores. These land grants were sold during the 19th century, and progressively if slowly developed for residential usage. Industry was relegated to the south and east, farming to the west. The industries included, most notably, abattoirs and rendering plants, quarries, railroads, locks, and electrical plants. Butchertown in the Dogpatch, India Basin, and northern Bayview, hosted the U.S.’ largest meatpacking district west of Chicago from the 1850s through the early 1900s. (See https://www.sanfranciscostory.com/a-photographer-in-butchertown/). There was a rock quarry at Cortland and Bayshore, one at Corona Heights, and a quarry at Candlestick Point up through the 1980s. Candlestick Stadium only broke ground in 1958. 

   Various light and heavy industry took much land on the east side-vast shipbuilding and iron works at Pier 70 in Dogpatch (now a National Historic District), rendering plants, the Schwerin electrical plant on the border with Daly City, and the Schlage Lock works in Visitacion Valley. The latter stayed in business during throughout the 20th century, closing only in 1999. The CEMEX Barge Aggregates Yard cement plant at Pier 92 remains open. Industry requires energy. Pacific Gas & Electric‘s Evans power plant closed in 2006, and the Potrero Power Plant in 2012. The PG&E Dogpatch power station remains.

Dense housing is a hallmark of the Eastern Neighborhoods as much as single family housing characterizes the West side. The historic heart of the city- the Tenderloin, Chinatown, Nob Hill, Russian Hill and North Beach- contain hundreds of apartment buildings, as well as public housing and in the remaining Single Room Occupancy hotels (in SoMa and Chinatown). South of Market is currently given over to a vast conference center, museums, an ice rink, bus station, and office buildings. However, in mid-century this neighborhood housed many of the city’s estimated 518 SROs, with 30,000 residents, which have been gradually eradicated. (“Between 1970 and 2000, the city demolished or converted to condos 15,000 SRO units”. The Bold Italic, Jeremy Lybarger; July 9 2014; https://www.todco.org/history.

Further south, the Federal government built a profusion of workers’ housing both for the Second World War and later. With the notable exception of the Western Addition and Japantown, this construction took place on the east side. The first was Bernal Heights’ Holly Courts housing project in 1940. This was followed by Potrero Terrace and Potrero Annex were built in 1941 and 1955, and are currently being redeveloped. The Candlestick Cove project was built in Visitacion Valley for HPNS workers, and demolished in 1954 to make way for Highway 101. Hunter’s View on Innes Avenue, adjacent to the Naval Shipyard, was built in 1956 and is currently being renovated. At Double Rock, near Candlestick Park, the city built both the old Alice Griffith in 1962 housing and the new Alice Griffith to replace it, immediately to its east, in 2018. In Visitacion Valley, the Geneva Towers was built in the 1960s, and demolished 1998. The expanded Sunnydale Housing Project covers the same location (https://www.hope-sf.org/four-communities/). (See: Visitacion Valley History Project. San Francisco’s Visitacion Valley. Arcadia Publishing. 2005. Also: Bernal History Project. San Francisco’s Bernal Heights. Arcadia Publishing. 2007).

San Francisco is no longer a major industrial city, but there is still a great deal of industry,
immensely skewed toward the East. A look at the San Francisco Planning Code and the Zoning Map (https://data.sfgov.org/-/Zoning-Map-Zoning-Districts/ibu8-4ccn) is highly instructive.

The current Municipal Code allows all manner of industry, permitted and regulated. The vast majority of heavy industrial usage remains in the east- including the cement plant, the Darling International rendering plant, and vast recycling facilities. Recycling and garbage collection includes, from north to south, the Southeast Water Treatment plant, old and new in the Bayview, the vast recycling plant at Pier 80, and Recology’s facility at Tunnel Road bordering Brisbane. Hunter’s Point started as a commercial shipyard in 1870. It was requisitioned as a Naval shipyard from 1939 through 1974. Most incongruent with a city, the Naval Shipyard also hosted the Naval Radiological Defense Laboratory, a legacy which left the vast areas of the Shipyard with polluted water and soil. Much has been said about this elsewhere.

The PDR-1-B light industrial buffer area (Sec 210.3 of the City Planning code), intended as a buffer between industry and residence, allows many uses which inevitably create AQ emissions.

(Municipal Code, Article 2 Use Districts. San Francisco Municipal Code last updated to include changes made by legislation through Ordinance 44-25, File No. 250069, approved April 3, 2025, effective May 4, 2025). Warehouses and storage facilities are permitted, most notably Amazon’s facilities and a controversial proposed Prologis facility. The San Francisco Gateway Project, which is moving through the approval process as of May 2025, in CEQA process, is not highly welcome in the neighborhood. These create immense truck and car traffic (https://48hills.org/2023/09/a-new-stealthy-amazon-delivery-center-on-the-edge-of-the-bayview/). While the special district in BVHP is intended as a buffer zone, this does not always satisfy those concerned with AQ.

Another and apparently less problematic cohort of industrial uses is commercial food distribution and kitchens. As visible on the SF City Department of Public Health List of Permitted Commissaries and Kitchens, the majority of the City’s permitted kitchens and wholesale food and restaurant supply, along with the San Francisco Farmer’s Market on Alemany, are near Oakdale and Bayshore.

The eastern neighborhoods south of the Financial District are also crisscrossed by numerous busy arterial auto and truck lines, both north-south and east-west in addition to the major highways. Both residential and commercial usage are far denser in proximity to these arterial routes- Mission Street, San Jose Avenue, Alemany Boulevard, Cesar Chavez, 16th and 24th Streets; Geneva, and Bayshore Boulevard- on the eastern side than on the west.

In summation, the majority of the eastern half of the city is extraordinarily economically productive, houses many people, and is highly burdened with commensurate concomitant pollution of all sorts. This is true both before the 20th century, but also after the First World War, and BVHP in particular is certainly more burdened since the start of WWII. In this context, the western neighborhoods are indeed Outside Lands, a suburb contained within the city. Bayview Hunters Point bears the brunt of the environmental burden for economically productive but highly polluting societal functions.

The Evidence of Air Quality

The land usage all but guarantees an abundance of anthropogenic aerosol air pollutants, both NAAQS and TACs. Many sources bear this out. The 2014 Community Air Risk Evaluation study and all four versions of Cal EnviroScreen prominently include large areas of the Eastern neighborhoods- BHVP, Visitacion Valley, San Bruno Avenue and parts of the Portola, and the Tenderloin. The larger area of the Eastern Neighborhoods is considered an Impacted Community, while the neighborhoods listed are within the top 15% of Pollution Vulnerability Index (p25). The CARE study Identifying Areas with Cumulative Impacts from Air Pollution in the San Francisco Bay Area (Version 2, March 2014) indicates that both the Air District’s method and the Environmental Justice Screening Method identify almost exactly the same areas. Citation: The CARE Study Impacted Areas Evaluation Methodology, and Identifying Areas with Cumulative Impacts from Air Pollution in the San Francisco Bay Area, Version 2, March 2014).

   More recently, the 2020 San Francisco Citywide Health Risk Assessment: Technical Support Documentation (SFDPH and Ramboll Sept 2020), is highly informative. Figures 10 and 11, p29 and 30, indicate high PM 2.5 contribution from mobile sources along the most heavily traversed highways in the city, especially the path of Highway 101. This exposure in turn leads to higher cancer risk in a nearly congruent pattern (Figure 11, p30). The APEZ maps of 2020 and 2025 (Map of Air Pollutant Exposure Zone | DataSF) included most of the Eastern Neighborhood (Air Pollution Exposure Zone Handout Feb 2025. SF Planning Department; San Francisco Planning, Air Pollution Exposure Zone Map 2020, 2025 revised). The APEZ map excludes Bernal Heights and Potrero Hill, as well as the easternmost sections of Hunters Point, but includes a large residential area bordering the Bernal Cut and Alemany Boulevard- Highway 280 as far as the border with Daly City near Mission Street and Junipero Serra. Rule 38 dictates MERV filtration over 13 required in new construction in said locations. However, this does not help current residents of buildings prior to 2009, nor pedestrians, drivers with the window down, shoppers, and transit riders. Information regarding Permitted facilities and Superfund sites is available on BAAQMD’s website. The map compiled in the Hidden Hazards report indicates inordinate recent and historical concentration of Hazardous Materials sites, as well as the Water Treatment Plant and the state Superfund Site at the HPNS. 

   The geographic skewedness of TAC and NAAQS emissions also applies should we look at emissions inventories. The California Emissions Inventory Data Analysis and Reporting System (CEIDARS) database offers evidence regarding the emissions of specific stationary sources in given zip codes. While CEIDARS stores information for stationary, areawide, mobile, and natural source pollutants, the facility search engine only offers queries for stationary point criteria and toxic pollutants. According to the Criteria and Air Toxics Reporting: 2021 Data Summary, the number of reporting facilities for both NAAQS and TACs is far higher in the Bay area than in any of the other Air Districts. The other AQMDs include San Joaquin Valley and the South Coast (Los Angeles), indicating that the Bay Area is far more industrially active than the general public may realize.

At a more granular level, examining the reported Emissions levels within municipalities- in this case San Francisco- is illuminating. The disparities in emissions of both NAAQS criteria pollutants and TACs between different stationary sources is stark. Examining the Criteria Pollutant Emissions Inventory CEIDARS Facility Search tool’s 2023 results by zip code, the highest levels of NAAQS in the City, by far, are found in Bayview and Dogpatch/ Potrero Hill (94124 and 94103). Among stationary sources, in 94124, Cemex Central concrete supply; (lines 12 and 13, File FAC 1), and to a much lesser extent Darling Ingredients (line 23 File FAC 1) produce a great deal of PM. In 94134, Recology on 501 Tunnel Avenue also produces PM, although nothing near the Cemex range (fac3). (The CARB Pollution Mapping Tool presents the same information, with a more accessible user interface).

Toxic Air Contaminant results are high, with emissions often from the same facilities that emit criteria pollutants in 94124 and 94134. Darling International, which has announced planned closure of its Bayview facility, emits 9.2 of formaldehyde. The new Water Treatment Plant at 1700 Jerrold, which was under construction during 2023 through 2026, emits the highest volume by far of Benzene and Di Benzene in a single facility in the City (fac10 and fac 4 file). TACs are also heavy in 94103, far downtown, and they are mostly car-related with the exception of formaldehyde and benzene produced by a natural-gas powered heating system (Cordia) on 460 Jessie Street (fac 5 and fac 6). Large commercial buildings including the Twitter Building, large hotels and apartment buildings, and the University of the Pacific Dental School all seem to produce a good deal of HCOH (fac 6).

AB 617 and Emissions Inventories

Pursuant to Assembly Bill 617 (C. Garcia, Chapter 136, Statutes of 2017), CARB established the Community Air Protection Program (CAPP) (https://ww2.arb.ca.gov › community-air-protection-pro...). Among other things, AB 617 mandates more uniform statewide reporting of emissions data to better track emissions reduction, However, it seems extremely difficult to find any information other than CEIDARS information regarding specific permitted facilities. The CEIDARS system appear to only include information for permitted sources. The HARP data module instructions are from 2017, the year that AB 617 was approved. Reading about the ongoing AB617 projects does not seem to indicate any changes to HARP’s (Hotspots Analysis and Reporting Program) Emission Inventory Module (EIM) CARB’s data entry tool, as a result of AB617’s CERPs.

West Oakland, the longest-running AB 617 community, has the emissions calculated in its CERP report by taking old baselines, then figuring out emissions reductions from BARCT implementation, they could extrapolate to ambient AQ improvements from AB617 emissions reductions plan. San Francisco’s plan is still being written, so we have no emissions data either from monitoring or modeled to refer to.

As part of the CERP process which AB617 set in motion, AB617 communities investigate AQ monitoring in their areas. There are several such ongoing monitoring projects in San Francisco.

AQ Monitoring in San Francisco

Several monitoring entities act on an ongoing basis in San Francisco: 

BAAQMD: FRM monitor for all NAAQS; 10 Arkansas Street only;

Purple Air: LCS monitors for PM 2.5; about two dozen locations in the EN; 

Clarity Open Map: non-regulatory monitors for NOx and PM 2.5; Alice Griffith; Hyde and Golden Gate; Carroll and 3rd Street; Innes; Kirkwood and Earl; UCSF Hunter’s Point; Oakdale and 3rd Street; UCSF Mission Bay; 10 Arkansas Street; 9th and Brannan; Howard and 6th Streets; Eddy and Jones; Clay and Kearny; UCSF Mount Zion; UCSF Parnassus; 
   We are awaiting historical data- which the Open Map does not provide.
 
Greenaction All Things Bayview PM 2.5 monitors, Dylos brand; several in the BVHP.

Berkeley Beaco2n: PM 2.5, CO2, CO, and O3 monitors; SFZGH, Exploratorium, SECF; (Other installations at the Hall of Justice and the SF Public Safety Building have been decommissioned as of June 2024).

Aclima/ Google Aclima used Google self-driving cars to transport mobile monitoring equipment as they traversed every street in San Francisco and a number of other communities. This information is, ostensibly, available to researchers. Manylabs/ SFAQ is waiting on a mid-June request for this data, followed up by another request in August.

Fenceline: various monitors

In addition, there is fenceline data collected as a matter of course at construction projects, and a very visible securely fenced monitoring installation near the HPNS entrance. It is unclear whether such data is available to the public in any way.

Health Effects of AQ

An inordinate record of health concerns, including those related to aerosol pollutants, has been recorded. The Hidden Hazards report indicates that a 2006 SFDPH survey which found that more than ¾ of children born in BVHP develop asthma by kindergarten age (p2).  Disparities in lung cancer incidence have been acknowledged by the SF Department of Public Health (p8). The Hunters Points Community Biomonitoring program (https://www.hunterspointcommunitybiomonitoring.net/ ) has found inordinately high toxic mineral content in blood and urine samples from Bayview residents and those who worked in the Shipyard.

Is there a way to reduce the AQI, maintaining the economic vitality? Many CARB measures try this, as do many BAAQMD measures. We will consider this question at the end of this report.

4. Project Description

San Francisco-based open science non-profit Manylabs/ San Francisco AQ’s Air Quality Network for San Francisco’s Eastern Neighborhoods, submitted to the California Air Resources Board, is a Supplemental Environmental Project.  We install, maintain, and display information online for air quality monitoring instrumentation to detect particulate matter 2.5 (PM 2.5) and Volatile Organic Compounds. PM 2.5 contributes to pulmonary and cardiovascular illnesses, and VOCs such as benzene, formaldehyde, and carbon tetrachloride inflict various health effects such as headaches, coughing and irregular heartbeat, and pose an incremental cancer risk. This project builds upon an earlier grant, which deployed monitors in the Eastern Neighborhoods, encompassing Bayview-Hunters Point, the Excelsior, Bernal Heights, Visitacion Valley, Portola, Balboa Park, the Dogpatch, and the Tenderloin and Chinatown.

4.1 Technical Approach

Our original focus on PM 2.5 monitoring was revised in light of new developments between the original approval and the time that the project was funded. AB617 legislation, assertively implemented, has provided funding and support to PM 2.5 monitoring funding for numerous California environmental justice communities, and required that they implement PM 2.5 monitoring, pandemics notwithstanding. 

   The progress made by Greenaction, the Marie Harrison Bayview Air Monitoring Project, and All Things Bayview has alleviated the need for hyperlocal PM 2.5 monitoring in the Eastern Neighborhoods. We have several Purple Air II monitors and are working with community-based organizations to deploy them in the Bayview. 

    Alterations to the original plans, confirmed in discussions with the Air Resources Board, allowed increased focus on VOCs, the carcinogenic properties of which are confirmed in the Federal NESHAPs and state's Toxic Air Contaminants inventory. Vinyl Chloride and H2s are measured in CARB lists, and H2S is measured at certain BAAQMD Federal Reference Method centers (Richmond, Point Richmond, and Rodeo).  Photo-ionization detectors required for VOC detection remain expensive, and such instrumentation has not typically been used in community air monitoring projects.

4.2 Sensor Instrumentation Plan

Manylabs/ San Francisco AQ acquired five Sensit SPOD non-regulatory instruments to test for TVOC and other indicia. Following initial co-location, these were deployed and gathered data in the Portola, central Bayview Hunters Point, and southern Bayview near San Bruno Avenue. One unit in the Outer Sunset neighborhood served as a control, and another was used for temporary deployment in various locations in the Tenderloin and the Outer Mission. Sensit Connect software managed data logging, and we used Excel, CSV files, Goggle Sheets, and the EPA’s Retigo software for data analysis and graphing. Deployment locations reflected community concerns, proximity to population centers and to near permitted facilities, and transportation corridors.

4.3 Initial Co-location  
   We set up the units on a rectangular outdoor patio ten feet above sidewalk level, about 18 feet west to east. The easternmost sensor was the closest to the street. We then co-located them in early May, 2023, prior to deployment across the city. All measurements were taken every 30 seconds. Downloads by Sensit Connect for this time period indicate strong although not perfect correlation. Unit 1427 data spiked immediately after installation, and then stabilized. Otherwise, the units generally performed well right out of the box. The mean of the values witnessed during May 1 through May 10. is 33.814 ppb; the median was 33.50 ppb, with a Min of 29.9, and a max of 40.35. The standard deviation of the values is 3.99, so the data are relatively close to the mean. The Github repositories with Excel Charts are located at rebeccaelizskinner/Air-Quality-Network-for-San-Franciscos-Eastern-Neighborhoods-May-2023-CoLocation-Data

The Data are as follows:

1507 48th Avenue: LAT 37.7582597; LON -122.5079587

1404

Avg = 33.5 ppb;

1507 48th Avenue: LAT 37.75822; LON -122.50813

1425

Avg = 29.9

1507 48th Avenue: LAT 37.75822; LON -122.50805

1426

Avg = 33.84

1507 48th Avenue: LAT 37.75817; LON -122.50807

1427

Avg = 40.35;

1507 48th Avenue: LAT 37.75824; LON -122.50806

1428

1507 48th Avenue: LAT 37.75821; LON -122.50809

Avg = 31.48

1404

Avg = 33.5 ppb;

1507 48th Avenue: LAT 37.75822; LON -122.50813

4.4 Data plan QA-QC
   Basically, quality control consisted of watching closely and checking on a regular basis. We excluded low values- or exclude the day if it was simply showed zero for hours on end.  We watched for spikes, often caused by the sensors losing power and then resetting, and then excluded that data. The easiest way to do this was by inserting a chart in MS Excel and then checking visually.

5. Implementation, and Issues therein

Siting

Despite our worries, selecting sites for stationary monitoring did not prove to be a significant issue. We wondered about a systematic approach to siting- since there are several different ways to approach this. Should we prioritize SPOD placement near permitted facilities, sensitive receptors, or high-VMT locations? Would the highest density of population be the best criterion?

   After much teeth-gnashing, we asked for a consultation with BAAQMD engineers familiar with the area. They said to simply pursue locations that were already well-known to the community.

It was gratifying that the scientific advice was what we would have wished to do regardless; 
Because we did not have that many sensors, siting was far easier than it might have been. Ironically, finding hosts was far more of a problem. However, our long-term monitoring sites reflected typical desiderata- Hudson Street was near a transportation corridor and permitted facilities;

Crane Street was in a very high VMT location; and the Tenderloin day placement addressed Density of population and significant AB2588 TAC issues.

Hosting
   If siting was easy, hosting was difficult. Finding community interest was no problem- AQ is on the minds of America in general and EJ communities in specific. The AB617 CSC, ATB and the BVHPEJTF are all actively concerned with AQ. But despite extant community groups studying AQ, finding hosts who would commit to hosting sensors was far more difficult.  

Data Collection and tools used

The Sensit SPODs were accompanied by the Sensit Connect data management and display tool. We checked this on a regular basis, and downloaded on a daily and monthly basis. 
The data was stored in GDrive and in Google Gmail folders, and the accompanying SD cards were downloaded as txt files, converted to csv files using Excel, and kept in GDrive and Gmail folders. We used the downloaded CSV files in Excel charts and in Google Sheets. Typically, Google Sheets was preferable for viewing summary statistics, and Excel was preferable for viewing line and column charts. Google sheets offered column stats, including characterization by column- maximum, minimum, median, and number of data points. Sensit Connect offered charts with comparative data options, to look at the readings of several sensors at once.

Data Integrity- Drift

As mentioned, we had more time than originally planned. This was auspicious, because data-gathering took more time than originally planned as well. The readings seemed meritorious- neither improbably low nor extremely high- for at least a year for most of the sensors. The 1427 units began reading at zero and was removed to the control site early in 2025. The 1426 unit started reading extremely high after April 2025. We were close enough to the end of the project, and had so much meritorious data gathered, that we simply stopped gathering new data.

6. Report on the Data

6.1. Summary

The results, inspected visually, show immediately evident patterns. On a persistent basis, the worst TVOC levels are those on Crane Street, a short street near Paul and the old Bayshore Boulevard and less than 0.2 miles from Highway 101. One and a half miles north, in central Bayview, we found lower average levels of TVOCs. For the purpose of this report, we define the Bayview Opera House as the center point in Bayview Hunter's Point. The next highest TVOC levels are those at Newcomb and Phelps, in central Bayview. Short-term community monitoring work at the sidewalk level in the Outer Mission and in the Tenderloin also indicated high TVOC levels. This suggests high point source levels near major point sources in the Eastern Neighborhoods.

Another deployment at Cargo Way and Third Street, on June 21, 2024, was sufficiently noxious that the participants had to stop the test and dismantle the equipment within an hour, even as the TVOC levels continued to increase. Granted, this is not a residential street. However, it is on a major arterial route with bus and light rail traffic into and from the Bayview, especially during commute hours. In addition, this location is .9 miles north of central Bayview.

The control unit, at 48th Avenue and Kirkham in the Sunset, had well-known point sources, in the form of the neighbor’s occasional sidewalk barbeque and campfire location across the street. These inflict weekly TVOC spikes on the immediate area. However, SFPD will not ticket a cooking fire contained with a structure. Street cleaning and garbage collection trucks incurred pollution spikes at predictable times.

The most minimal TVOC levels were found in the six-month backyard deployment on Goettingen Street near Wayland Street. This hosting site, which ran from June, 2023 through January, 2024, showed such consistently low readings that the unit was removed. 

   Another site with consistently and unexpectedly moderate TVOC levels was Boedekker Park, at Eddy and Jones Street (March 6, June 12, September 13, 2024). In both cases, a setting in a backyard or location with significant distance (approximately fifty feet) from the point source emissions of vehicles seems to allow enough distance for volatile aerosols to experience mass transport. 
 
6.2 Exposition regarding Different Locations

Please see attached Excel charts for each location. Github repository:

rebeccaelizskinner/https-github.com-rebeccaelizskinner-Air-Quality-Network-for-SF-Eastern-Neighborhoods--Sites: Exposition regarding Monitoring Sites

1. 48th Avenue at Kirkham Street
   This deployment was located on a street-facing second-floor outdoor patio, approximately ten feet overhead. Car traffic was approximately ten to fifteen feet away. Because of proximity to the ocean, only one block to the west, there is frequently a low breeze. This low-level turbulent air flow would tend to encourage low pollutant levels. However, local point sources changed that. Later in 2024, new construction projects in the large apartment building to the northeast, diagonally across the street, increased local TVOCs (and probably PM 2.5).

2. Crane Street- Paul at Bayshore

This deployment was located in the backyard of a two-story house, with several trees but no grass. Crane Street is a small and quiet route adjacent to three significant transit corridors. These are in ascending order- Paul; Bayshore and Highway 101 (less than .2 miles away). The local point sources are clearly evident. Car and bus traffic on Paul Street runs continuously. Bayshore Boulevard- known as “the Old Bayshore Boulevard” since the elevated Highway 101 immediately adjacent follows its route inside San Francisco- is a six-lane surface arterial street immediately to the east of 101 and thus, even closer than 1/5 mile to Crane Street.
The 450,000 square feet diesel-powered data center across the street from Crane Street operated through the end of 2023. It went through a duty cycle in which exhaust was disgorged, at some time between 0900 and 1000 weekdays.

This site had by far the highest TVOC levels of the sites studied, including persistent high background levels. Levels were most dramatic in the winter months. In December, reached over 100ppb ambient readings. This approached the NIOSH STEL level of 150 ppb.

3. 1700 Block, Newcomb Street at Phelps
   Like Goettingen and Crane Streets, this deployment was located in the backyard of a two-story house, with significant foliage, one and a half blocks from Third Street. Local point sources abound. The Southeast Treatment Plant, built in 1952 and handling 80% of the city’s storm water and wastewater, is currently being redeveloped as the Biosolids Digester Facility. Work to remodel it started in the Spring of 2020. REF TO THE CEQA 2018 OR 2016 DOCUMENT; 

4. The Portola: Goettingen Street at Wayland

Portola is known as the Garden District, as announced by the billboard at the entrance to the area's freeway onramp at San Bruno and Silver Avenues. This nomenclature is vindicated by the low TVOC levels, and low variability in levels, at the six-month deployment in the Portola. The backyard sensor, in a backyard with trees and a lawn bordered by neighbors’ similarly green backyards, returned mundane and quotidian readings. We took this sensor down in January 2024, after gathering six months of data.

The distance from this spot to Crane Street is 6/10ths of a mile, or a brisk ten-minute walk.

5. Hudson Avenue at Mendell Street

This backyard deployment is situated on a quiet street a block and a half from the Youngblood-Coleman Playground and the same distance from Third Street. Car traffic appears to be largely local, and it is six-tenths of a mile to Cargo Way at Amador. The house in question is immediately adjacent to a car repair facility (across the back fence, to the immediate north). Despite this, readings were moderate rather than severe.

6. Mobile day deployments: Boedekker Park

Boedekkker Park, at 196 Eddy Street, is a beloved local park, in perhaps the grittiest urban location in San Francisco. It is located at Eddy and Jones Streets, diagonally facing a police station, and an auto body shop across the street to the west, and a garage across the street to the south. Local point sources abound, especially from cars that may not be in compliance with smog checks. However, AQ readings (on March 15, June 12, and September 13, 2024) were middling rather than precarious. We suspect that this is explained by the roughly fifty-foot distance between the testing location and the sidewalk.

7. Mobile day deployments: 175 Golden Gate Avenue

Meanwhile, a few hundred feet away, streetside measurements vindicate our concerns. At the sidewalk at 175 Golden Gate Avenue, all data points were all above 100 ppb. The distance is 0.3 miles by surface streets, although less as the crow flies (December 10 and October 24, 2024).

8. BVHP mobile day deployments: 1550 Evans at Newhall Street

On June 7, 2024, the project conducted a morning community monitoring event, along with All Things Bayview, on the sidewalk at Evans Avenue at the corner of Newhall. We found relatively low ambient TVOC levels- higher than nearby Hudson at Mendell Street, on a wide street with significant air flow and steady but moderate traffic.

9. BVHP mobile day deployments at 3rd Street and Cargo Way

This is a thoroughly noxious location from the vantage point of AQ, and we only were able to tolerate it for just under an hour. Fortunately, very few people live within a quarter mile. Unfortunately, thousands of people use 3rd Street, in the immediate vicinity to drive, wait for the train or bus, and walk. The irony was the fact that the pollutant that drove the researchers away was not VOCs!  This site is one-third of a mile from the SECF. 

10. Geneva Avenue and Mission Street

Readings took place a few feet from a gas station at 891 Geneva Avenue on February 25, 2025. All readings were above 100, some near 200. The corner of Geneva and Mission is a heavily residential neighborhood, with low apartment buildings on all four sides. The Outer Mission is well-served by bus transit, and heavily traversed by cars as well.  

6.3 Summary Statistics and Time Series Averages

Using Excel and Google Sheets, we examined the data using summary statistics. Basically, December is the highest TVOC month; Spring months are the lowest. The hottest months- August, September, and October- also have high TVOC levels. In the attached chart, we present the monthly averages for the Central and Southern Bayview SPODs.

Attach Bar Chart: Average TVOC ppb Monthly, Central and Southern Bayview.

Summary statistics are of use here. We omit the minimum, which will always be zero, and the median. The modal value, however, is valuable because it discounts the value of spikes.

The attached bar chart indicates that Newcomb Street and Crane Street had the most consistently high TVOC readings- notably, in the winter months. In December 2024 in particular, average monthly readings for both of these sensors were in the vicinity of 150 pbb. PPB readings for both Newcomb and Phelps, and Crane Street, both near blatantly obvious point sources, were often around 50ppb in the Spring and through July.

In contrast, we include a bar chart with Goettingen Street- one half-mile from Highway 101 and the Bayshore Boulevard- as well, to indicate how very low these levels were. The Hudson- Mendell site, despite its location, did not have unduly high readings. Islais Creek is roughly ½ mile away, and this finding suggests that TVOCs do not diffuse that far. TVOC’s travel, but not very far. In contrast, the Newcomb Street site is only one-tenth of a mile away from the Water Treatment Plant, and Crane Street is a similar distance from Bayshore Boulevard.

Average monthly readings in 48th Avenue began to increase with the commencement of steady construction work immediately across the street and sidewalk barbeques hosted by a neighbor. These findings suggest that ambient TVOCs are highly hyperlocal in effect.

Unlike NAAQS pollutants, VOCs do not have minimum tolerable standards the exceedance of which incurs non-attainment. Thus there is no FRM or FEM instrumentation with which to correlate readings. Thus, we do not consider r2 regression measures to be necessary, since there is no testing against the reference monitor. Since this is a time series, we don’t see the need for standard deviation testing, the t test, ANOVA, and covariance. Central tendency will be foiled by daily conditions- at the very least temperature changes at night, midday, traffic conditions. For instance, we expect readings at 0200 and 1400 at to be different. We did carry out

correlation tests which we will examine later.

Github: rebeccaelizskinner/Air-Quality-Network-for-San-Francisco-s-Eastern-Neighborhoods-Charts-and-Spreadsheets: Manylabs/ San Francisco AQ's Air Quality Network for SF's Eastern Neighborhoods- Charts and Spreadsheets for Report

6.4 Diurnal Trends

Generally, the range of readings for TVOC did not vary a great deal over the course of a day. This is in marked contrast to PM 2.5 readings. In most cases PM 2.5 peaks between one pm and four pm, for instance at the SFAQ 1550 Evans Street Southeast Community Facility monitor, for instance. TVOCs typically form through a secondary process in response to sunlight, as well as being an emissions product formed from various TAC sources. Quantitatively, the relative diurnal discrepancies can be assessed by observing the summary statistics for the range between measurements for each of these days. The range was generally larger for the sensor units in which there are salient point sources or high local background levels. We noted some increase, for instance from 20 to 40 ppb, during the mid-day, followed by a reversion back to the lower levels, in most cases. See Appendix 9.1 Diurnal Trends. Since O3 is also a secondary pollutant, it would be interesting to see ozone levels in these vicinities.

Diurnal Data w sunrise and sunset times;

August 11 2024; 06:29 sunrise, 20:24 sunset;

1428 Paul and Bayshore variation 50 to 80 ppb, but no spikes

1427 Newcomb Phelps 20 to 40 ppb, no spikes nor secular increasing trend;

1425 Hudson Mendell 40 ppb steady

1404 48th Ave at Kirkham 30ppb, very little change;

Sept 14 2023,

1427 Newcomb Phelps slight increase mid-day (1300 1600) but only from 40ppb to 70 ppb;

1425 48th Avenue at Kirkham readings peaked mid-day but only to 15 ppb;

March 7 2024 0632 1810
1404 Hudson Mendell increases, to 40 ppb during mid-day;

1427 Newcomb Phelps slight increase mid-day, 32ppb to 40s; 
1425 at 48th Avenue at Kirkham 18 ppb, up to 60s in mid-day but then back down;

Github: rebeccaelizskinner/Air-Quality-Network-for-San-Francisco-s-Eastern-Neighborhoods-Diurnal-Data: Diurnal Data for Air Quality Network for San Francisco's Eastern Neighborhoods Project

6.5 Correlation between TVOC and Temperature, Relative Humidity, Air Pressure, and Wind Speed 

   Are there notable correlations between TVOC PPB and Temperature, relative humidity, atmospheric pressure, and wind speed? We carried out eighteen instances of correlations using Microsoft Excel’s CORREL function.

   There was a positive correlation between TVOC ppb and Temp in every case we examined but one. The TVOC ppb to temperature correlation, was at least 0.6 and was often much higher.

   We did not test at high temperatures because it is simply never very hot in San Francisco. Truly high temperatures were few, and far between, in 2024, and this is no different from other years. Until October 1, there were no temperatures above 90f. October 1 hit 90f, and October 5, 95f. Most temperatures are moderate: in November, there were no readings over 70f or below 45f; in December no readings over 65f or below 45f. Even in, January 2025 there were no readings over 65f, or below 40f. We did not test at temperatures below about 40f degrees because these lows are also unheard of locally. The February minimum of 41f and the August maximum of 85f would not impress millions of Americans elsewhere. We are well aware that most of the continental USA, and much of the world, has it far worse. This is consequential for AQI and AQ. Higher high temperatures present considerable worry from the perspective of AQ, since ozone formation is secondary to atmospheric TVOC.

HOTTEST MONTH: Sept;

COLDEST MONTH Dec 3 to Feb 4;

The other correlations- Relative Humidity, Air Pressure, and Wind Speed- are negative, or non-linear with a weak positive slope at certain high values.

Relative humidity correlates inversely to ppb TVOC levels- except in the case of rain, in which case it is weakly positive for ppb TVOC. Atmospheric pressure correlates negatively to ppb TVOC in most cases, although the Bay Area does not have extremes in mBar. Wind speed correlates inversely to TVOC ppb. This is however a much weaker relationship with correlations below 0.5. Barometric pressure and wind speed may be confounding variables in any effort to construe TVOC levels and temperature in a causal fashion. Temperature could be an independent variable and TVOC dependent- but this will be confounded by the other two variables.

How does this look in light of increasingly volatile weather? Any implications are more marked for many areas other than the SF Bay Area- since one of the area’s chief attributes is its dearth of dramatic weather. More dramatic rain storms- presents no worry from an AQ perspective given there will be downwash. (Of course, downwash affects water and soil quality, so its overall environmental effects should not be dismissed). We do not appear to have inversion events with both high atmospheric pressure and high temperatures. The City would not appear to have the topography for it anyway.

7. Conclusion and Policy Suggestions

7.1 Significance of the Findings

As we saw, there were indeed higher TVOC levels in the Eastern Neighborhoods in the form of slightly higher background levels relative to readings in a West Side street with little car traffic, and no other obvious things such as fugitive emissions from construction. But the BVHP readings were not uniformly higher than those in other areas. More emphatic is PM 2.5 readings. BVHP is indeed afflicted with a host of environmental maladies and health conditions, but in this case decades of EJ injustices did not manifest in high TVOC levels. Historical pollutants, such as those remaining in polluted water and soil near the Superfund site, do not seem to result in high ambient TVOC levels.

Several specific findings- and subsequent questions- should be highlighted.

The distinct and often-noted odor in the vicinity of Islais Creek was not TVOC affecting the residential areas. It would not be surprising, though, if it were hydrogen sulfide (H2S), because of current presence of Darling International. One other historical observation is that this is the historic site of Butchertown, and very close to the water table. Much of the area between Hudson and Third Street west to Highway 101 just north of Silver Avenue is listed on the SF Water Power Sewer 100 Year Flood map as an historical waterbody. The eastern edge of the Eastern Neighborhoods consists of estuaries and wetlands. The Vadose zone- that is, the area between the surface of the ground and the water table- becomes more active with slow but inevitable immutable ongoing sea level rise.

This leads to questions that are out of the scope of our project and air quality questions more generally. Is this land prone to inundation, and is it highly composed of landfill? If so, does land like this often emit H2S? Is the odor commonly spoken of H2S leaching from the soil? If so, soil remediation is a technically sophisticated field of practice has been conducted in more noxious environments. These questions, requiring answers from a hydrologist, are well worth asking.

The typically high TVOC levels in Central Bayview near the Water Treatment plant’s residential neighbors- 142ppb in December 2024 in Newcomb Phelps- makes clear the emphatic need for countervailing adsorptive measures to mitigate both TVOC and PM 2.5. The new BioSolids Digester Facilities plant will be accompanied by Community benefits to remediate the inevitable, but this area still maintains concerns over PM 2.5 and TVOC.

Southern Bayview, adjacent to San Bruno Ave immediately proximate to Highway 101 and to Bayshore Boulevard, experienced high ambient TVOC in winter months. Some of the readings were above 100ppb ambient. This was also the case with the sidewalk monitoring events at 891 Geneva Avenue at Mission, and Golden Gate and Leavenworth. The average winter measurements at Crane Street (Paul and Bayshore) were over 100 (144 in December 2024 and 102 in December 2023)- not far below the WHO 200 ppb measurement STEL. These levels were not STEL according to WHO standards, but the possibility of cumulative health effects should not be dismissed. 

   Meanwhile, measurements at Hudson and Mendell Streets- a half-mile from Islais Creek- at Evans and Newhall, and at 48th Avenue during 2024, prior to a large construction project nearby- were unremarkable. Backyard measurements and those in areas with high air flow, setbacks of buildings from streetside vehicle traffic, and moderate traffic flow seem to ensure relatively low TVOC measurements.

Instead, the real issue with respect to TVOCs is in areas near 1) industrial concerns and 2) areas of high VMT. Proximity to ongoing VMT rather than historic permitted facilities presents more of a problem.  The punch line- and it is not funny- is that this means a giant swathe of the Air Pollution Exposure Zone maintains high TVOC too. This constitutes a great portion of the residents of the city, rather than only environmental justice neighborhoods or those designated CARE. 

   Much of the City is not represented on Cal EnviroScreen 4.0, and much of City still features on the APEZ and commensurate air pollution sensitivity. The APEZ map areas stretch from the Ferry Building north to Van Ness, east to Japantown, and southwest to the Castro. All areas adjacent to Caltrain, Bayshore Boulevard, Alemany and Highway 280 are included. One caveat appears to be clearly due to topography: practically every hilltop throughout the entire city appears to be exempt from APEZ designation.

   We must tend our gardens, but the issue of just how much reduction in emissions the EN has control over remains frustrating. Those freeways will not shut down in any imaginable future, and both ICE and EV vehicles are highly polluting.

7.2 The Way Forward: Monitoring Suggestions

Further consideration of ambient TVOCs, and specifically street-side monitoring in the Air Pollution Exposure Zone is warranted, then. There is no Low-Cost Sensor equivalent of the Purple Air for TVOCs, this task would ideally be the remit of an Air District or CARB itself. Sidewalk monitoring in particular seems fit for larger teams over the course of an entire day, something that is nearly impossible with a much smaller project.

We have discussed these measures with CBO; political will to follow up would be required on the part of those who live and vote in the area.

7.3 Policy Suggestions

Our measures as proffered have been said and done before, and are thus quotidian, but they do remain to be said. The way to approach this is to use extant methods, but also to lean into the weeds, so to speak, of measures that can be implemented by the City and regional Agencies. We suggest a variety of measures in the areas of State-level rules; City agency rules; public health (DPH) and community engagement actions; and modifications of the built environment, in that order.

A. Reduce Vehicular Emissions

This suggestion is made with the caveat in mind- there are major highways and arterial roads in the Eastern Neighborhoods. This leads to the next suggestion- again, mobile source policy is set at state and federal agency level.

The site with the highest background TVOC levels is 0.20 miles from a four-lane arterial route and interstate Highway 101 traversing San Francisco north-south. Emissions from these venues cannot be addressed by municipal or regional air district policies. However, national and state policies to remove antiquated vehicles from the road and tighten emissions standards could alleviate emissions, as could increased adoption of EVs.

B. Planning- modifications to extant Rule 38

Health Code Article 38, established in 2008, requires enhanced indoor air filtration in new construction in areas near heavy traffic (see Article 38 Rules). There is an elaborate Planning Department method to determine this map (Air Pollutant Exposure Zone), which added some areas near roadways in the 2025 version. However, this doesn’t help current residents, or many residents of the Eastern Neighborhoods.

Yet the IAQ enhancements of Article 38 could be implemented in an even larger scale. The Production Distribution and Repair districts- the Bayview light industrial area, well as the PDR zones in the Dogpatch, Southern Bayview, and SoMa- take up very large areas. The Planning department could modify PDR zones by requiring the same updated indoor AQ filtration rules as Rule 38 Air Pollution Exposure Zones (map attached).

C. SFMTA and Diesel truck routing
   Another possibility is the rerouting of diesel trucks so as to minimize proximity to population centers in the Eastern Neighborhoods.

D. Traffic Calming

Local vehicular traffic within the immediate vicinity seems to be highly consequential for TVOC levels, and is probably the main source of pollutants at the control sensor location in the Sunset district. However, traffic calming can be implemented without the higher authority of CARB.

Cities in general, and San Francisco in specific, can stop sideshows and donuts, preferably when they take place, install speed bumps, and ticket the infamous and polluting “Dirtbike Gang” and grand polluter vehicles. However, it seems loathe to do so.

E. Education regarding Household and Indoor TVOCS
   The San Francisco Department of Public Health has previously given presentations on household pollutants. Common household chemical products are often founts of airborne VOCs. It would be worthwhile if presentations such as one the DPH gave at the SF public library on August 3, 2024, was a frequent event.

F. Urban Heat Island Mitigation Measures

Urban heat island mitigation measures might improve both NAAQS and TAC/ NESHAP air pollutant levels as well. Measures such as cool pavements and green roofs, bio-treatment planters, rain gardens, and vegetation cover streetside, are taken to cool hard pavement and near-blackbody road paving materials. Green infrastructure is typically presented as a benefit to water quality (precipitation, sidewalk water) or for temperature amelioration, but it would be surprising if it did not also have inadvertent air quality effects. Both ozone and VOCs form as a secondary process, enhanced by heat, so heat island mitigation measures could have Air Quality co-benefits as well.

G. Tree Planting

Based on the discrepancy between measurements streetside and those in backyards on deep lots (125’), it seems that local trees and plants ameliorate the presence of ambient TVOCs.

This is already known as regards PM 2.5, and simply suggests that it applies to TVOCs as well.

It is not clear if the mechanism is absorptive (involving the pollutants chemically taken into the tree) or adsorptive (the PM sticks to the surface). This adds to the chorus of those suggesting trees be planted as a general means to improve AQ. San Francisco even has an official list of approved Trees (https://www.sfenvironment.org/recommended-tree-lists?repaired), and local groups such as the Friends of the Urban Forest have planted trees on sidewalks for more than 30 years.

H. Vegetative barriers

Another modification of the built environment is not trees but shrubbery or ivy. Vegetative barriers are under study as enhancements to dry deposition, adsorption and absorption of PM 2.5 and VOCs. See Barwise and Kumar, Lee et. al., and Ghasemian et al 2017.

I. Artificial ‘Trees’ and Adsorptive Materials
   Notwithstanding the merits and aesthetic appeal of trees, activated carbon adsorptive materials and best industrial (BARCT) practices such as industrial filters and scrubbers added to stacks are less aesthetically and conceptually friendly but should be considered in ambient pollutant mitigation. We suggest this even though the pollutant levels even in a highly polluted residential location are lower than in the highly concentrated levels in an industrial setting.

8. References

Yendle Barwise and Prashant Kumar.“Designing vegetation barriers for urban air pollution abatement: a practical review for appropriate plant species selection”. Climate and Atmospheric Science (2020): 3:12.
https://doi.org/10.3389/ffgc.2023.1301533

Lee, Jongkyu, Myeong Ja Kwak, and Soo Young Woo.“ Adsorption of particulate matter and uptake of metal and non-metal elements from PM in leaves of Pinus densiflora and Quercus acutissima: a comparative study.” Front For. Glob. Change, 04 January 2024. Sec. Forests and the Atmosphere

https://doi.org/10.38/s41612-020-0115-3. 

Lee, Jongkyu, Myeong Ja Kwak, and Soo Young Woo.“ Adsorption of particulate matter and uptake of metal and non-metal elements from PM in leaves of Pinus densiflora and Quercus acutissima: a comparative study.” Front For. Glob. Change, 04 January 2024. Sec. Forests and the Atmosphere https://doi.org/10.3389/ffgc.2023.1301533

https://escholarship.org/uc/item/3881b3q5 Authors Ghasemian, Masoud, Amini, Seyedmorteza, and Princevac, Marko.” The Influence of roadside solid and vegetation barriers on near road air quality”. 2017.

San Francisco Zoning Map https://data.sfgov.org/-/Zoning-Map-Zoning-Districts/ibu8-4ccn.

Visitacion Valley History Project. San Francisco’s Visitacion Valley. Arcadia Publishing. 2005.

https://www.hope-sf.org/four-communities/

Bernal History Project. San Francisco’s Bernal Heights. Arcadia Publishing. 2007.

https://www.sanfranciscostory.com/a-photographer-in-butchertown/

https://www.nps.gov/safr/learn/historyculture/buried-ships-of-san-francisco.html

https://www.sfenvironment.org/recommended-tree-lists?repaired

Recommended Street Tree List.

APEZ maps of 2020 and 2025 (Map of Air Pollutant Exposure Zone | DataSF)

Air Pollution Exposure Zone Handout Feb 2025. SF Planning Department; San Francisco Planning, Air Pollution Exposure Zone Map 2020, 2025 revised.

West Oakland Community Emissions Reduction Plan.

Municipal Code, Article 2 Use Districts. San Francisco Municipal Code last updated to include changes made by legislation through Ordinance 44-25, File No. 250069, approved April 3, 2025, effective May 4, 2025.

ALA State of the Air report. April 25, 2025.

July 25 26 27 2023. EPA Conference on QA QC for AQ

April 3 4 10 17 24 2024 EPA Webinar series on AQM.

2014 CARE study.

CEIDARs Facility Search Engine. 

Anne Steinemann.” Ten questions concerning air fresheners and indoor built environments”. Building and Environment 11 (2017): 279-284.

Jason G. Su et al." Examining air pollution exposure dynamics in disadvantaged communities through high-resolution mapping”. Science AdvAnceS research article 2024. adm9986 (2024) 7 August 2024. 

Kornhuber, Kai et. Al. “Global Emergence of regional heatwave hotspots outpaces climate model simulations”. PNAS Research Article. Vol 121, No 49. 2024.

Jiayi Fan, SFSU Master’s thesis. 2015.

APEZ Map. Air Pollutant Exposure Zone (2020) Map. SF Planning Dept.

Nelson A. Roque et. Al. “Identifying air quality monitoring deserts in the United States” PNAS Research Article Environmental Sciences. 2025. 122, no. 17.

San Francisco Citywide Health Risk Assessment, Technical Support Documentation. SFDPH. February 2020.

EPA AQ sensor toolkit

US EPA Office of Air Quality Planning and Standards. Technical Assistance Document for the Reporting of daily air quality- the Air Quality Index (AQI). EPA 454/B-18-007. September 2018.

CAPCOA PQAO doc?

Cohen Research - University of California Berkeley. Berkeley Environmental Air-quality & CO2 Network (BEACO2N). Available at http://beacon.berkeley.edu. Date accessed: [July 24, 2024].

Retigo and AirData EPA sites.

Thomas D Sharkey, Amy Wieberley and Autumn R. Donohue.“ Isoprene emission from plants: Why and how”. Annals of Botany, 101 (2008): 5-18.

Su et. al." Examining air pollution exposure dynamics in disadvantaged communities through high-resolution mapping". Science Advances 10 Research Article. eadm9986. 7 August 2024. Shan Zhou et. al.“The effects of temperature and humidity on the VOC emission rates from dry building materials”. 2019 IOP Conf. Ser.: Mater. Sci Eng. 609 042001

Github data repositories:

rebeccaelizskinner/Air-Quality-Network-for-San-Francisco-s-Eastern-Neighborhoods-Report: Report for Air Quality Network for San Francisco's Eastern Neighborhoods Project

Air Quality Network for San Francisco’s Eastern Neighborhoods / Charts and Spreadsheets

rebeccaelizskinner/Air-Quality-Network-for-San-Francisco-s-Eastern-Neighborhoods-Charts-and-Spreadsheets: Manylabs/ San Francisco AQ's Air Quality Network for SF's Eastern Neighborhoods- Charts and Spreadsheets for Report

Air Quality Network for San Francisco’s Eastern Neighborhoods / Photographs

rebeccaelizskinner/Air-Quality-Network-for-San-Francisco-s-Eastern-Neighborhoods-Photographs: Manylabs/ San Francisco AQ, Air Quality Network Project- Photographs accompanying Report

Diurnal Data

rebeccaelizskinner/Air-Quality-Network-for-San-Francisco-s-Eastern-Neighborhoods-Diurnal-Data: Diurnal Data for Air Quality Network for San Francisco's Eastern Neighborhoods Project

Colocation Data

rebeccaelizskinner/Air-Quality-Network-for-San-Franciscos-Eastern-Neighborhoods-May-2023-CoLocation-Data

9. Appendices

9.1 Diurnal Trends

rebeccaelizskinner/Air-Quality-Network-for-San-Francisco-s-Eastern-Neighborhoods-Diurnal-Data: Diurnal Data for Air Quality Network for San Francisco's Eastern Neighborhoods Project 
Diurnal Data w sunrise and sunset times;

August 11 2024; 06:29 sunrise, 20:24 sunset;

1428 Paul and Bayshore variation 50 to 80 ppb, but no spikes

1427 Newcomb Phelps 20 to 40 ppb, no spikes nor secular increasing trend;

1425 Hudson Mendell 40 ppb steady

1404 48th Ave at Kirkham 30ppb, very little change;

Sept 14 2023,

1427 Newcomb Phelps slight increase mid-day (1300 1600) but only from 40ppb to 70 ppb;

1425 48th Avenue at Kirkham readings peaked mid-day but only to 15 ppb;

March 7 2024 0632 1810
1404 Hudson Mendell increases, to 40 ppb during mid-day;

1427 Newcomb Phelps slight increase mid-day, 32ppb to 40s; 
1425 at 48th Avenue at Kirkham 18 ppb, up to 60s in mid-day but then back down;

Other Diurnal Days of Interest 
2. 5 0648 1752

7 17

6 13 0547 2033

6 7 1550 Evans

6 21 Cargo Way;

9.2 Correlations Data

rebeccaelizskinner/Air-Quality-Network-for-San-Francisco-s-Eastern-Neighborhoods--Correlations-Data

February 25, 2025 am;

1426 at Geneva and Mission; 891 Geneva;

N= 1464;  Ppb avg 114; RH average= 47.28 Temp avg 18.1, is 64.5f

C: E temp CORREL -0.557 n=1400

C:F RH 0.70785

C:G mBar Pressure; 0.57466
C:H Wind Speed -0.1716

December 10 2024
175 Golden Gate Avenue at Leavenworth; 
N= 1071; n=1000

Ppb avg 105; RH average= 58.84 Temp avg 14.64, is 58f; Avg mBar Pressure = 1022.8; Average Ws 0.32

C: E temp CORREL 0.4837 n=1000

C:F RH -0.4191

C:G mBar Pressure; -0.316
C:H Wind Speed -0.051; that is, no relationship;

July 1, 2024

It did not rain but was extremely humid (weather Underground and world weather);

C: E temp CORREL 0.7814 n=2000

C:F RH -0.75686

C:G mBar Pressure; -0.33815
C:H Wind Speed 0.22211

October 1 2024 highest temp of the year;

#1428 Paul Bayshore n=2000
C: E temp CORREL 0.9018 n=2000

C:F RH -0.89123

C:G mBar Pressure; -0.2133
C:H Wind Speed 0.8779

October 5 2024 close to highest temp of the year;

#1428 Paul Bayshore n=2000
C: E temp CORREL 0.8225 n=2000

C:F RH 0.1771

C:G mBar Pressure; -0.248
C:H Wind Speed 0.8779
ppb average 142
Temp average 24.4c 75.9f

N= 2800

Feb 4 2024 atmospheric river;
#1428 Paul Bayshore n=1000
C: E temp CORREL 0.7117

C:F RH 0.1163

C:G mBar Pressure; 0.20806
C:H Wind Speed -0.17063

January 31, only rainy day in January 2025

January 24, 2025 Humid;

#1428 Paul Bayshore n=4000
C: E temp CORREL 0.8621 n=2000

0.8621 n=4000

C:F RH -0.8595

C:G mBar Pressure; 0.9068
C:H Wind Speed -0.3877

Feb 27, 2025 hottest day in 2025;

#1428 Paul Bayshore 
C: E temp CORREL 0.6579 n=2000

0.63858 n=4000

C:F RH -0.6635  n=4000

C:G mBar Pressure; -0.6125  n=4000
C:H Wind Speed 0.3515   n=4000

Nov 25 2024 rain;

Nov 22, 2024 heavy rain;

#1428 Paul Bayshore n=4000
C: E temp CORREL 0.171

C:F RH 0.211

C:G mBar Pressure; 0.1870
C:H Wind Speed -0.357
was there not much variation in C TVOC pbb over the course of the day?

Feb 5, 2025 rain; most of the day, 1.35”

#1428 Paul Bayshore n=5000
C: E temp CORREL -0.175535

C:F RH 0.31051

C:G mBar Pressure; 0.1811
C:H Wind Speed -0.018
RH average 67.06;

Ppb Avg 80

Temp average 9.4c, 48.9f;

Feb 13 2025 rain;

#1428 Paul Bayshore 
C: E temp CORREL 0.43763, n=4000

C:F RH 0.275066

C:G mBar Pressure; -0.679

March 12, 2025 atmospheric river; 
#1428 Paul Bayshore 
C: E temp CORREL 0.3204, n=3000 and n=4000

C:F RH -0.4436

C:G mBar Pressure; 0.7047
C:H Wind Speed 0.0318

SPOD Data Aug 11 2024 1428 Paul Bayshore correlation: TVOC ppb and temp: 0.725482

SPOD Data Aug 11 2024 1428 Paul Bayshore correlation: TVOC ppb and RH: -0.68651

SPOD Data Aug 11 2024 1428 Paul Bayshore correlation: TVOC ppb and barometric pressure: 0.120

SPOD Data Aug 11 2024 1428 Temp Max 23.3, Min 12.2; average 15;

SPOD Data Aug 11 2024 1428

n = 2000 rows;

SPOD Data March 7 2024 1425 48th Ave correlation: TVOC ppb and temp: 0.992

SPOD Data March 7 2024 1425 48th Ave correlation: TVOC ppb and RH: -0.9638

SPOD Data March 7 2024 1425 48th Ave correlation: TVOC ppb and pressure: 0.69979

n = 2000 rows;

n = 1000 rows;

SPOD Data March 7 2024 1427 Newcomb Phelps correlation: TVOC ppb and temp: 0.84966

SPOD Data March 7 2024 1427 Newcomb Phelps correlation: TVOC ppb and RH: -0.8274

SPOD Data March 7 2024 1427 Newcomb Phelps correlation: TVOC ppb and pressure: 0.8215782
n = 3000 rows;

SPOD Data March 7 2024 1427 Newcomb Phelps correlation: TVOC ppb and temp: 0.7927

Temp average 12.4, min 7.9, max 18.7

TVOC ppb average 32.5, med 32.8

n= 1000

SPOD Data October 2024 1425 Hudson Mendel 
n= 2000

correlation: TVOC ppb and temperature: 0.7512

n= 10,000

correlation: TVOC ppb and temperature: 0.61692

n= 2000

correlation: TVOC ppb and RH: -0.6146
n= 10,000

correlation: TVOC ppb and RH: -0.6428

average TVOC ppb monthly, 91ppb;

SPOD Data September 2024 1428 Paul Bayshore

n= 2000

correlation: TVOC ppb and temp: 0.567

n= 2000

correlation: TVOC ppb and RH: -0.5417
n= 2000

TVOC ppb and pressure: 0.19121

SPOD Data October 2024 1428 Paul Bayshore

n= 2000

N= 84,077

correlation: TVOC ppb and temp: 0.901

correlation: TVOC ppb and RH: -0.891
Av 90.7

Max 566

Med 84.92

SPOD Data February 25, 2025 1426 891 Geneva at Mission

n=1400, N=1467

correlation: TVOC ppb and temp: -0.557
correlation: TVOC ppb and RH: 0.7078
TVOC ppb and pressure: 0.5746

9.3 Governmental Air Quality Guidelines for VOCs

VOC regulations

OSHA: OSHA has adopted a Permissible Exposure Level (PEL) of .75 ppm, and an action level of 0.5 ppm. 

HUD: The US Department of Housing and Urban Development (HUD) has established a level of 0.4 ppm for mobile homes.

NIOSH TVOC STEL 150ppm, 560 mg/m3

EH40 (United Kingdom) TVOC

Hong Kong TVOC <600 ug/m3, 0.30 ppm

Germany TVOC <0.66 ppm moderate or good;

WHO Air Quality Guideline:

>0.10 ppm to 0.20 harmless;
>0.20 ppm to 0.61 temporary exposure only;

Well Building Standard
TVOC  <500 ug/m3, , < 0.25 ppm

LEED Leadership in Energy and Environmental Design. 
TVOC <500 ug/m3, < 0.25 ppm

RESET Standard- Air for Commercial Interiors:
< 0.25 ppm acceptable;

Renesas IAQ Rating:
Medium quality: less than 1.0 mg/m3

Fitwell Enhanced Indoor Air Quality Testing and Monitoring Protocol 
TVOC <500 ug/m3

US EPA Building

1700 ml volume, or 1.7 l

100 ppm is high isob,

100 ppm is 1 per 10,000 or .1 per 1000;

100 ppm is 0.0001 of a million;

.5 lpm;

.1 liters every 12 seconds; or 0.0588235 as % that is .1/ 1.7

.05 liters every 6 seconds; will be 0.0294117 as % that is .05/ 1.7

both of the latter are much more than 100ppm;

.025 liters every 3 seconds; will be about 0.0145 as % that is .025/ 1.7

1/1700 is .000588235

30.6 mL is LEL;

30.6 mL is 0.0306 Liter;

Molhave L., Clausen G, B Berglund et. al." Total Volatile Organic Compounds (TVOC) in Indoor Air Quality Investigations". Indoor air.1997; v7. 225-240.
Atmotube: 
“Translation from mass concentration ug/m3 to particle concentration ppb is based on an average molar mass of TVOC molecules, according the TVOC mix proposed by Molhave 1997. Thereby 4.9 ug/m3 corresponds to 1 ppb TVOC concentration.”

Renesas Electronics. Overview of TVOC and indoor air quality. Dr. Christian Meyer. White Paper. May 21, 2021.

Environmental science and Technology briefs for Citizens.

German Federal Environmental Agency
Bundesgesundheitsblatt- Gesundheitsforschung Gesundheitsschutz 2007, 50: 990-1005. Springer Medizin Verlag 2007.

AQ Guidelines for Europe; hg. v WHO Copenhagen 2000. 

Indoor air quality management group of Hong Kong.

Kansas State U. Volatile Organic Compounds (VOC) and Consumer Products Regulations

eCFR : 40 CFR Part 59 Subpart C -- National Volatile Organic Compound Emission Standards for Consumer Products.

9.4 List of California TACs.

10. Acknowledgements

For their time, advice, and dedication to the people of the Eastern Neighborhoods, we would like to thank the Bay Air Center, Bradley Angel, Rickie Cleere, Kamillah Ealom, Michael Flagg, Arianne Harrison, Marie Harrison (in memoriam), Kate Hoag, David Holstius, Anthony Khalil, Blair Lapin, Jennifer Ly, Leotis Martin, Ken McGary, David McKinley, Javier Padilla, Peter Palmer, Karen Pierce, Michelle Pierce, Hadrian Picq, Helena Plizka, David Ralston, Tonia Randall, Peter Sand, Steven Tennis, Steven and Oriana Tiell, Raymond Tompkins Jr., Chris Whipple, and the San Francisco Community Ambassadors.

Volatile organic compounds (VOCs) are also defined as those which have a Reid vapor pressure above 10.3 Pa at ambient temperature (293.15 K) and pressure (101.325 kPa).

Reid vapor pressure (RVP) is “the absolute vapor pressure exerted by the vapor of the liquid and any dissolved gases/moisture at 37.8 °C (100 °F) as determined by the test method ASTM-D-323”. Wikipedia.

https://archive.epa.gov/ttn/ozone/web/html/def_voc.html.

EPA - TTN NAAQS - Ozone Implementation - Technical Resources - Definition of Volatile Organic Compounds (VOC).

Zhang et. al. 2017 p102.

World Health Organization. WHO Guidelines for Indoor Air Quality: selected pollutants. WHO: Copenhagen, Denmark. 2010.

https://www.epa.gov/haps

https://ww2.arb.ca.gov/resources/documents/carb-identified-toxic-air-contaminants. Also https://leginfo.legislature.ca.gov/faces/codes_displaySection.xhtml?sectionNum=39655&lawCode=HSC, and https://oehha.ca.gov/air/general-info/toxic-air-contaminant-list-staff-reportsexecutive-summaries.

Shumin Cheng et al." Global Research trends in Health Effects of Volatile organic compounds during the last 16 Years: a Bibliometric analysis". Aerosol and Air Quality Research 19. 2019: 1834-1843.

Galezowmska, G., M. Chraniuk, I. Wolska." In vitro assays as as tool for determination of VOCs' toxic effect on respiratory system: a critical review". Trac-Trend Anal. Chem. 77 (2016) 14-22.

Galezowmska, G., M. Chraniuk, I. Wolska." In vitro assays as a tool for determination of VOCs' toxic effect on respiratory system: a critical review". Trac-Trend Anal. Chem. 77 (2016) 14-22.

B. Huang, C. Lei, C. Wei, G. Zeng." Chlorinated volatile organic compounds (Cl-VOCs) in environment- sources, potential human health impacts and current remediation technologies". Environ. Int. 71 (2014) 118-138.

P. Patnaik, A Comprehensive Guide to the Hazardous Properties of Chemical Substances. John Wiley & Sons. 2007.

Zhang et al 2017 has an excellent summary on health effects of VOCs.

Godish p412.

www.epa.gov/nata.

K. Ard. “Trends in exposure to industrial air toxins for different racial and socioeconomic groups: a spatial and temporal examination of environmental inequality in the U.S. from 1995 to 2004”. Soc Sci Res, 53. 2015: 375-390.

K. Zwickl, M Ash, and K Boyce. “Regional Variation in environmental inequality: industrial air toxics exposure in U.S. Cities”. Ecol. Econ. 2014. 107: 494-509.

R Atkinson Gas-phase tropospheric chemistry of volatile organic compounds: 1. Alkanes and alkenes”. J Phys Chem Ref Data 26 (1997) 215-290.

Spinelle, Gerboles, et. Al.” Review of Portable and Low-Cost Sensors for the

Ambient Air Monitoring of Benzene and Other Volatile Organic Compounds”. Sensors. 17, 1520. 2017. p1.